## RcaEda
MAKE SURE TO ENABLE MACROS BEFORE EDITING THIS SPREADSHEET Heading
Case Number | Product | Abstract Headline |  |  | Assessors |  |  | Quality Reviewer | [5 empty] | Current State | Do Not modify
02169604 | Flexi Multiradio BTS SingleRAN | Post AEHC replacement (SRAN21A 3.0) DL User Throughput, E2E CSSR, ERAB DR, VOLTE DR degraded, UE lost cases increased, UL User degraded 30 %. |  |  | Yu Zhiwei, Xuan Juwei, Zhang Yijie, Lei Enqing, Guo Jun |  |  | . | [5 empty] | Assigned | these 2 Cells
Gather Facts |  | Facts
1. Issue Description What was the problem from the customer's or tester’s viewpoint? What was wrong or not working? |  | throughput degraded 30%
2. Triggering scenario What sequence of events is needed to observe the fault? What environment (e.g. HW/SW configuration) should be used? What constraints should be satisfied? Where and how was the issue actually found? Repeatability %% |  | AEHC 20 UE per tti without pair
Triggering scenario category: select appropriate item from the list |  | SW Upgrade
3.Code Deficiency: What was wrong in the source code? Short technical description like *variable was overwritten due to queue overflow --> The check for queue size was wrong - did allow more entries than actually fit into the queue “name of non-existing file was sent to iOMS” --> “No check for file creation operation success was performed” |  | some of FCP msg was dropped -> number of section per layer exceeded limitation -> unpaired ue were all located on one layer
4. Correction Description: How the code was changed to fix the issue? Just a short technical description: *variable was overwritten due to queue overflow --> The check for queue size was wrong - did allow more entries than actually fit into the queue --> “queue size verification was added” “name of non-existing file was sent to iOMS” --> “No check for file creation operation success was performed” --> “file creation operation result is verified before next actions” |  | distribute unpiared ue to layer 0 and layer 1 averagely.
5. Injection type - New Feature - Defective Correction - Optimization / Refactoring - Revealed Issue - Legacy code See Technical RCA guideline for detailed description: https://sharenet-ims.inside.nokiasiemensnetworks.com/Overview/D492583158 |  | New Feature Development
6. Injection time When the issue was merged (precise date) and first build containing the issue (e.g. LN4.0_ENB_1202_476_42) + following: - For New Feature injection: Feature ID - For Defective Correction injection: PR id - For Legacy Code: latest file revision (date) which was checked to claim Legacy Code |  | SBTS21A_ENB_0000_001875_000000 LTE3950
7.Additional Facts - Was the issue corrected in another branch and not propagated to the branch where the issue was detected and reported by Customer? - Any other facts worth to be mentioned If case of a doubt (should be mentioned or not) – please do add the information |  | issue was found and fixed on 21A. PR608804 was reported on 21B, 22R1 and trunk, issue was fixed by it.
8.Inheritance Recommendation - Should the issue be requested for propagation in maintenance branches? - Guidenace is to request inheritance for issues which might lead to an outage (e.g. rolling reboot, sleeping cell, site unavailability, site visit is needed to repair after the fault occurence and etc) |  | 21A
9. How many times R&D requested for Symptoms/Logs recollection (number)? |  | 0
Review Fields
Root Cause Analysis | Why 1 |  | Why 2 | Why 3 |  | Why 4 |  | Why 5 | Root Cause | Action Proposal | Root Cause Category | Root Cause Subcategory | RCA Action Type | Assigned To | RCA AI ID | Completion Target Date
Why was the fault introduced? (Process RCA) See Process RCA guideline for information how to proceed | why: locate all unpaired ue on layer 0 answer: CFAM did not explicitly specify how to distribute ue on layers, and legacy code locate all unpaired ue to layer 0 |  | why: CFAM did not explicitly specify how to distribute unpaired ue on layers answer: CFAM didn't realize it's necessary to distribute unpaired ue to different layers due to mac ps capability larger than l1 low. In fact, this issue was detected at 21B and fixed, but 21A missed. | why: CFAM didn't realize it answer: l1 low capability was defined in a separated doc, it was not metioned in CFAM |  |  |  |  | l1 low capability was not defined in CFAM | add l1 low capability and how to distribute unpaired UE in EFS | Requirements | Missing Requirement | Requirements Improvement | angela.liang@nokia-sbell.com |  | 2021-11-30
|  |  |  | why: 21A was not fixed after 21B fixed answer: we considered if 21A would have the same issue, but l1low gave us a wrong answer. |  |  |  |  | l1 low capability was not defined in CFAM, we considered if 21A would have the same issue, but l1low gave us a wrong answer. | lessons learn workshop: 1.l1 low capability limitation 2.how to distribute unpaired ue 3.when do the impact anlysis, need involve SC Arch | Requirements | Missing Requirement | Requirements Improvement | zhiwei.1.yu@nokia-sbell.com |  | 2021-11-30
Why root cause was not found with first set of attached symptoms? (see CDI Guideline) Mandatory if there was at least one symptoms/log re-collection requested
Use these arrows and lines
Do Not erase or Move this box
[7 empty] | Can only Add columns after "Why 5" (col K) when adding more whys |  |  | Review Fields
Escape Defect Analysis | Why 1 |  | Why 2 | Why 3 |  | Why 4 |  | Why 5 | Escape Cause | Action Proposal | Escape Cause Category | Escape Cause Subcategory | EDA Action Type | Assigned To | RCA AI ID | Completion Target Date
1. Why didn't Requirements reviews catch this defect? | Not apply. refer RCA.
| Why 1 |  | Why 2 | Why 3 |  | Why 4 |  | Why 5 | Escape Cause | Action Proposal | Escape Cause Category | Escape Cause Subcategory | EDA Action Type | Assigned To | RCA AI ID | Completion Target Date
2. Why didn't Design reviews catch this defect? | Not apply. there is no such requirement
| Why 1 |  | Why 2 | Why 3 |  | Why 4 |  | Why 5 | Escape Cause | Action Proposal | Escape Cause Category | Escape Cause Subcategory | EDA Action Type | Assigned To | RCA AI ID | Completion Target Date
3. Why didn't code analysis tools such as Klocwork, Purify, etc catch this defect? | Not apply. It's a run time issue.
| Why 1 |  | Why 2 | Why 3 |  | Why 4 |  | Why 5 | Escape Cause | Action Proposal | Escape Cause Category | Escape Cause Subcategory | EDA Action Type | Assigned To | RCA AI ID | Completion Target Date
4. Why didn't code inspections catch this defect? | Not apply. there is no such requirement.
| Why 1 |  | Why 2 | Why 3 |  | Why 4 |  | Why 5 | Escape Cause | Action Proposal | Escape Cause Category | Escape Cause Subcategory | EDA Action Type | Assigned To | RCA AI ID | Completion Target Date
5. Why didn't unit or component test catch this defect? | UT can not catch this defect, there is no such requirement. SCT also can not catch this defect, no requirement define, refer RCA.
| Why 1 |  | Why 2 | Why 3 |  | Why 4 |  | Why 5 | Escape Cause | Action Proposal | Escape Cause Category | Escape Cause Subcategory | EDA Action Type | Assigned To | RCA AI ID | Completion Target Date | Where Could Defect Have Been Detected
6. Why didn't Entity Test test catch this defect? | ET have case designed to cover the scenario: 16 UEs scheduled per TTI interworking with 3CC CA MU, but it was blocked by another fault--PR603559: [TDD][ECPRI][ABIN][AEHB] Two sleeping cells on 3CC, so we prioritize other no run cases first, 02169604 have been raised and fixed when we try to retest this test case after PR603559 got fixed. Currently, no same issue is observed on CRT testing.
Why didn't ET automated test cases catch this defect?
| Why 1 |  | Why 2 | Why 3 |  | Why 4 |  | Why 5 | Escape Cause | Action Proposal | Escape Cause Category | Escape Cause Subcategory | EDA Action Type | Assigned To | RCA AI ID | Completion Target Date | Where Could Defect Have Been Detected
7. Why didn't System Test catch this defect?
Why didn't ST automated test cases catch this defect?
ARROW ToolBox
Use these arrows and lines
to show the chain-of-thought
between the whys.
Do Not erase or Move this box

## EDA Drop-down Descriptions
Triggering Scenario
Triggering_Scenario_LIST
Installation & Startup | These 5 cover items before the system has made a call
SW Upgrade
SW Fallback
Process of Configuration / Reconfiguration
Not Supported Configuration
OAM Operations | These 2 cover faults in normal modes of operation
Feature Interaction & interoperability
OAM Robustness (high Load / stressful scenarios/long duration) | These 2 cover faults in abnormal modes of operation
Telecom Robustness (high Load / mobility /stressful scenarios/long duration)
Debug (Counters/Alarms/Trace/Resource monitoring) | These 2 cover faults in reporting and recovery
Reset & Recovery
HW Failure | These 2 cover hardware derived faults
Required customer/vendor specific equipment
Unknown triggering scenario | Catch-all
Escape Type
Why Was Defect Not Detected
Configuration missing/misunderstood/incomplete | These 3 cover areas where we did not specify, or have test cases - Nokia did not think of this
Scenario missing/misunderstood/incomplete
Extraordinary scenario – Very difficult to recreate defect
Customer documentation not reviewed/tested | These 5 cover areas where we did specify, but the test case did not test the specification
Functional Testcase missing/misunderstood/incomplete
Non-Functional Testcase missing/misunderstood/incomplete
Regression Testcase missing/misunderstood/incomplete
Robustness Testcase missing/misunderstood/incomplete
Test Blocked : Lack of Hardware/Test Tools | These 6 cover areas where we did specify, did have test cases, but did not run the test
Test Blocked : Needed SW not available
Test run too early in the release
Planned Test run post delivery
Planned Test not run
Out of Testing Scope
Insufficient testing of changes/fixes | These 5 cover areas where we did specify, did have test cases, ran the test cases, but still missed the fault
Insufficient test duration/iterations
Fix was available but was not delivered
Incorrect analysis of test result, marked passed when actually failed
Intermittent defect
Where could Defect have Been Detected | Comments
earliest testing phase
Unit / System Component Test (UT/SCT) | All testing before Entity
Entity Test - Regression | Regression testing at entity level
Entity Test - New Feature | New feature testing at entity level
System Test - Regression | Regression testing at system level
System Test - New Feature | New feature testing at system level
Interoperability Testing | Covers intervendor operations
Performance Testing | Tests typically for performance KPIs and performed with high loads
Stability Testing | Tests with long cycles
Negative/Adversarial Testing | Any tests with non-standard inputs. "Torture" the system under test.
Network Level Testing | Full network testing with real Core, eNB, iOMs and NetAct
First Office Application | Customer testing in Live-Network
Injection Type Values
New Feature Development
Defective Correction
Optimization / Refactoring
Revealed Issue
Legacy code
Other

## CategoryData (hidden)
Category Type (RCA or EDA) | Reviwed Date | Reviewed Month | Category

## Version & Instructions
Tool Administrator: Pat Muirragui - Pat.Muirragui@nsn.com
Needs to be completed
| Revision | Comments | Date | Author |  | Instructions: | Used to resync <State> & <Current State> to correct wrong entries
| 01 | First Release | 2012-01-20 | pmuirragui |  |  | Only available to tool administrator
| 02 | Various changes, including removing limitations on adding rows | 2012-01-22 | pmuirragui |  | • Enter RCA/EDA information in <RcaEda> tab
| V2.0 | First release that posted to the RCA/EDA Practice folder. Ready for deployment. | 2012-01-23 | pmuirragui, J.Zahn |  | • Basic information: in Row 3, Columns C-O (Note: L-O are filled out as these dates are achieved)
| V2.1 | Added Dynamic Range names to MacroParms tables - Added Assigned and Assessed dates to every row in Summary table. | 2012-01-30 | pmuirragui |  | • Facts: in Row 5-14, Columns D-K
| V2.2 | Added Cause Category definitions to the Instructions worksheet | 2012-02-01 | J. Zahn |  | • RCA Details: in Row 21-25, Columns C-Q (Note: N-Q are filled-out as these dates are achieved)
| V2.3 | Suppresses 'xx' in <Approved Date>, Modified Error Message & corrected erasing of shState when transition from Assigned -> Reviewed. Sync with DX200_2_3 | 2012-02-29 | pmuirragui |  | • EDA Details: in Row 33-62, Columns C-Q (Note: N-Q are filled-out as these dates are achieved)
| v2.4 | Modifications to add 'Target date' field to each action - in Sync with DX200 V3.0 (Minor Cosmetic changes to match DX200 V3.0) | 2012-03-13 | pmuirragui
| v3.0 | Added "Closed Target Date" field to the Actions section, added Action Type Category Definitions. | 2012-03-19 | pmuirragui, J.Zahn
| v3.02 | Changed type of cells in matrix from Date to General, added banner to remind users to enable macros | 2012-03-20 | J.Zahn
| v3.03 | Restamped 'Reviewed Date from Date variable; added 'General' formatting to Summary tab columns 'F:L'. Removed 'Assigned' & 'Assessed dates for multiple rca/eda rows - no longer needed since it is replicated in rpmStatus tool. | 2012-04-06 | pmuirragui |  | • Ensure that after any change to the <RcaEda> tab, the <Summary> Table is updated.
| v3.05GLTE | Added data validation to date cells in the RCA and EDA Matrices, will help avoid issues with incorrectly entered date strings. Added GLTE specific changes. | 2012-04-06 | J.Zahn |  | • Store this file in its designated location
| v3.06 | Added code to write results of a root cause or escape cause if there is data in cause cell or any to the right of cause cell. | 2012-04-25 | J.Zahn
| v3.07 | Added "Should Have Been Found In" and changed "Symptoms" section | 2012-10-21 | F. Kunkel
| v3.08 | Updated "Should Have Been Found In" field | 2012-11-30 | F. Kunkel |  | Other instructions on template use can be fould in the slides at
| v3.09 | Updated CDI section and added CDI category values | 2013-07-15 | R.Gorski |  | https://sharenet-ims.inside.nokiasiemensnetworks.com/Open/D439793493
| v3.10 | Disabled SumAnaly macro on file save. Added email lists starting in col I of MacroParms. Added pulldown list to cell k3 of RcaEda. Added macros to send the emails with specific content per the 3 buttons. | 2013-07-29 | J.Zahn |  | Please note: The link to Harmonized RCA/EDA Values' instruction will be updated as soon as possible
| v3.11 | Disabled mail buttons unless product = TDD or WMP/FDD. Mail to lists now dependent on product (cell C3) type. | 2013-08-22 | J.Zahn
| v.3.51 | Updated TDD email receivers | 2014-07-28 | vdh483
| v.3.6 | Updated version change I&V to Entity Test / ET and System Verificarion / syve to Sytem Test / ST, new fields Triggering scenario category, Where Could Defect Have Been Detected, How To Avoid In Future , new list items for Escape Type in ET and ST EDA | 2017-12-06 | T. Kuhn
| v.3.6.1 | Update of EDA Trigger scenarios | 2018-01-04 | T. Kuhn
| v.3.7 | Update after Review | 2018-01-08 | T. Kuhn
| v.3.7.1 | Minor Update: removal of already selected escape type in ET section / reordered Drope-Down Lists Descriptions | 2018-01-08 | T. Kuhn
| v.3.8 | Implementing two-level and harmonized RCA/EDA values, including Root Cause Categories/ Subcategories, Escape Cause Categories/ Subcategories, Root Cause Improvement Actions, Escape Cause Improvement Action, Updating Instructions Accordingly | 2019-03-05 | A. Razmi Farooji
Root Cause Category | Root Cause Subcategory | Description |  |  | Root Cause Improvement Actions | Description
Requirements | Changing requirement | The requirement was changed but the change was not communicated to all teams affected or was communicated too late. |  |  | Requirements Improvement | Such as Improving communication/ collaboration with customers, Identifying the impacts of changes and communicating them with R&D/ Testing teams, Improving Requirement Template/ Checklists to make sure requirements are not missed.
| Customer specific configuration or traffic requirements not accounted for | A customer specific configuration, corner case or traffic condition was not included in the documented requirements and hence not considered during design or test. |  |  | Architecture Improvement | Such as Performing an architecture analysis, including Robustness and Stability(based on applying DFMEA), introducing domain specific training. Involving in reviews the right stakeholders who have knowledge about features and feature interactions, etc.
| Missing requirement | A specific requirement was missing from the requirements document, including functional, non-functional or robustness requirements. |  |  | High-Level Design Improvement | Such as Supplementary documentation for design study, Introducing domain / product specific training, Add the missed item to the design templates and/or design checklist (e.g. feature interactions / corner cases / error cases, etc.)
| Incorrect requirement | The description in the documented requirements contains a specific, factual error. |  |  | Low-Level Design Improvement | Add the missed item to the low-level design template/checklist / review (e.g. handling input, corner cases, buffer memory management, race conditions etc.), Introducing low-level design specific training
| Unclear requirement | A customer requirement was unclear, leading to an incorrect assumption during development and/or testing. |  |  | Coding Quality Improvement | Improving or adding to the coding standard/guideline. Improving or adding to the code review checklist. Process changes to ensure a code review is completed with the required reviewers.
| Misunderstood customer requirement | The requirement was clear. However, the requirement was misunderstood during specification. |  |  | User Documentation (including Release Note) Improvement | Such as testing user documentation, actually testing each procedure in the documentation. Ensuring customer facing teams review the documentation.
| Late added feature(s) | The added feature was not originally planned for actual SW delivery, and therefore, feature interactions were missed or developed SW was not tested properly. |  |  | Configuration and Fault Management Improvement | Automation of current manual processes to avoid manual mistakes with wrong code delivery to a given branch. Ensure there is adequate analysis and planning to avoid merge issues such as errors in a multiple feature merge or defect porting. Ensure all relevant fault managers are involved in planning the defect porting.
| Standards interpretation error | A requirement from the standards document was not correctly interpreted, leading to a design/test error. |  |  | Knowledge/ Expertise/ Training Improvement | Improving the product, domain, architecture, platform, technology, etc. knowledge. Training on development processes and supporting tools ( such Git, static analysis tools, etc.)
Architecture | Interworking error - feature or component interaction. | The impact of a new feature on other elements of the system was not fully explored or addressed.
| Memory consumption error | The defect led to a memory error, typically leading to memory leak. |  |  | Escape Cause Improvement Actions | Description
| CPU overload error | A CPU overload error that causes a system crash or causes an internal overload mechanisms to trigger |  |  | Technical Reviews Improvement | Typical improvement actions relate to making sure that the technical review is completed on time and involves the right stakeholders with the necessary knowledge and experience for the review. It can also involve putting in place or improving the tools used to support reviews by geographically distributed teams.
| Software robustness error | A specific failure mode, corner case, error case or stress scenario was not considered as part of the architecture. These are typically identified through DFMEA. |  |  | Code Analysis Tools Improvement | Typical improvement actions relate to making sure the static and dynamic analysis tools are run. When running static analysis tools, the tool settings must be correct and all errors identified must be fixed.
| Stability error | A memory, CPU or I/O error that only becomes visible over time, typically leading to symptoms such as system crash or sleeping cells. |  |  | Unit Test Improvement | Typical improvements are actions to ensure that mandatory unit testing is completed before submission and that the unit test covers all of the code, including error paths.
| Architecture gap | An aspect of the architecture was not sufficiently considered leading to an error in the software’s behavior or performance. |  |  | System Component / Module Test Improvement | Typical improvements are actions to add test cases for example missed tests, missed feature interaction tests, corner cases or error case/rainy day testing
| Architecture specification error | A factual, specific error in the architecture document |  |  | Entity/ Integration and Verification Test Improvement | Typical improvements are adding test cases. Teams should consider what test would have caught the escaped defect, for example module, sub-system or feature interaction tests, corner case tests or rainy-day tests.
High-Level Design | Hardware compatibility | Software is not compatible with the hardware in use. |  |  | System Verification Functional Test Improvement | Typical improvements are adding test cases. Teams should consider, based on the escaped defect, what other test cases, test types or triggering scenarios may have been missed, such as exploratory or robustness testing.
| 3rd party compatibility / interoperability | Software is not compatible with the 3rd party software which is part of the overall solution. This includes compatibility with 3rd party software the within platform. |  |  | System verification Non-Functional Testing Improvement | Typical improvements are adding non-functional test cases as well as adding robustness and exploratory tests
| Legacy interaction error | The interaction between new features and legacy features leads to an error.
| High level design missing/gap | There is no high level design document or there is a gap in the high level design document.
| Design error | A specific error in the high level design, resulting in an error in the software's behavior.
Low-Level Design | Low level design missing/gap | There is no low-level design document or there is a gap in the low level design document.
| Deficient design/design error | A specific error in the low level design resulting in an error in the software's behavior.
| Design knowledge, skills, competence (timer management, buffer handling, etc.) | Defect caused by poor implementation due to gaps in knowledge around low level design, including such areas as buffer and timer management.
Code | Code too complex | The structure of the system, module or component made it difficult to understand and modify without inserting faults. The fault originated as a result of the module, component or system complexity.
| Coding logic error | A specific error in the software logic, typically an error compared to the design.
| Coding language knowledge/expertise | Defect/error caused by insufficient training or expertise in the specific language used to implement the code.
| Coding standards violations | Defect/error caused by a specific violation of the coding standards that should be applied for the project.
| Implementation missing | The specific code needed to implement the function/feature is missing.
| Implementation error | If parts of the specification are not implemented as intended, implementation errors occur.
User Documentation (including Release Notes) | Incorrect information used to create End-User Documentation | The end user documentation, was created based on incorrect or out of date information.
| Missing content/ step in procedure | The end user documentation, is missing a specific section/procedure. A step in the documented procedure is missing, resulting in a defect/error.
| Missing detailed content (delivered content not sufficient from user PoV) | The contents of the end user documentation, does not contain all the of the details to enable the user to execute the procedure without error.
| Outdated content | The contents of the end user documentation is not up to date with changes made to the software.
| Language error | Error due to a language mistranslation in the user documentation
| Incorrect information in the change note | A specific factual error in the change note.
| Inconsistency within the same customer document | There is a conflict between two pieces of information within the same user documentation.
| User documentation not tested | The user documentation was not tested before release. Testing in this case means actually executing the commands as described in the user documentation to verify that the commands are correct.
Configuration and Fault Management | Build error/ incorrect version | Defect was caused by the wrong content delivered or used in given software branch on component or entity level.
| Merge error | Default parameter value changes not propagated to other releases as needed. Software configuration management tool merge issues such as in a multiple feature merge, where one feature over-wrote the other.
| Missed defect inheritance or porting process error | Defect was caused by a previous fix not being ported or inherited to a specific software branch.
Collaboration with Suppliers | Delivery failure | The delivery from the supplier was unacceptable in terms of content or quality, including software, specifications or test data.
| Lack of specification | Defect is caused by a missing or insufficiently detailed specification, either originating in Nokia or with the supplier.
| Documentation failure | There was an error in the user documentation provided with the 3rd party software.
| Implementation failure | The 3rd party software has an error in the implementation of the requirements.
| Lack of testing | The software delivered by the supplier was not sufficiently tested.
| Missing requirement | A feature/function expected in the software was not delivered.
| Project management | The committed features/functions were not delivered on the agreed date.
| 3rd party software limitations | The 3rd party software has a limitation or constraint. This can be a functional constraint or a non-functional constraint such as performance, scalability etc.
Escape Cause Category | Escape Cause Subcategory | Description
Technical Reviews | Requirements not reviewed with customer | Defect caused by a difference between customers understanding of the requirements and Nokia’s understanding of the requirements.
| Internal requirement review gap | There was no internal requirements review or one of the internal stakeholders did not participate in the requirements review.
| Architecture review gap | There was no architecture review or one of the internal stakeholders did not participate in the architecture review.
| Design review gap | There was no design review or one of the internal stakeholders did not participate in the design review.
| Missing analysis of impact of change | There was no analysis of the impact of a specific change or the analysis did not identify all of the possible components affected.
| Code review gap | There was no code review or the code review was insufficient. Tools to support code review were not available/ not used.
| Test strategy review gap | There was no test strategy review or one of the critical stakeholders did not participate.
| Unit or component testcase review gap | There is a gap or error in a specific unit or component test case that would/should have been detected by an independent review of the testcase(s).
| Entity or integration test review gap | There is a gap or error in the integration testing that would/should have been detected by an independent review of the testcase(s).
| System testcase review gap | There is a gap or error in the system testing that would/should have been detected by an independent review of the testcase(s).
| CuDo internal review gap | There was no review of the Customer Documentation or the review was insufficient.
Code Analysis Tools | Test tools availability/ capability | Testing was not performed, due to testing tool was not available or did not support the implemented feature. Testing was postponed to a later test phase, due to unavailability of test tools.
| Inappropriate tool usage | Code analysis tool was run, however the tool settings were not appropriate or not all of the errors flagged were corrected.
| Insufficient use of static analyzers | Either static analysis was not run or the necessary rule was not part of the rules.
| Insufficient use of dynamic analyzers | Either dynamic analysis was not run or suppression rules were suppressing a real error instead of a false positive finding.
Unit Test | Code not covered by test | The specific code path that caused the defect was not covered during unit test.
| Wrong check in testcase | Unit test did not verify correctly the end state or the interactions during the test.
| Stubs or mocks do not reflect real world scenarios. | Production code works against stubbed or mocked counterpart. But the stub or mock acts differently than the real-life counterpart.
| Objects initialized with wrong values | Initial state of objects used in the test does not correspond to real life scenario, for example if some initialization method was not run.
| Error cases/paths not tested | The specific code generating the error/defect is triggered by the software handling an error case or failure path and this error case was not tested.
System Component / Module Test | Functionality not covered | There was no test covering the functionality.
| Feature interaction coverage gap | Test scenario for tested feature (A) worked in normal case but it got broken when another feature (B) was activated. Interaction of features A and B was not covered in SCT.
| Corner case and error case test gap | Defect could have been detected with a corner case test or an error/ rainy day test.
| Limitation of test framework or environment | Test framework or environment did not support creating a proper test for the functionality.
| Configuration coverage gap | Test was not run in the specific configuration, in which the defect occurred.
| Test did not execute the planned scenario | Test behaves differently than intended. The executed scenario was different and the functionality seemed to work (while it did not).
Entity/ Integration and Verification Test | Requirement coverage gap | The fault came from a scenario or a function that had no requirements and no test case
| Limitation of test framework or environment | Test framework or environment did not support creating a proper test for the functionality.
| Configuration coverage gap | Test was not run in the specific configuration, in which the defect occurred.
| Test did not execute the planned scenario | Test behaves differently than intended. The executed scenario was different and the functionality seemed to work (while it did not).
| Exploratory testing (negative, sequence, abnormal, boundary, corner case) gap | Exploratory testing for software robustness was not completed or the specific error case/corner case was not tested.
System Verification Functional Test | Network or solution verification testing gap | A test case to detect the specific escaped defect did not exist, or
| Regression test gap | it does exist but was not run or not sufficient to detect the fault.
| Configuration coverage gap | A test case to detect a fault from a previous release or feature build was not run or did not exist
| Requirement coverage gap | A particular configuration necessary to find the fault is not available in the test labs
| Feature interaction coverage gap | The fault came from a scenario or a function that had no requirements and no test case
| Exploratory testing (negative, sequence, abnormal, boundary, corner case) gap | The fault came from a feature interaction that was not specified and had no test case
| Testing of UE software | Exploratory testing for software robustness was not completed or the specific error case/corner case was not tested.
| Insufficient Testing of 3rd Party SW/HW | Defect was contained within 3rd party software and the component containing the defect was not sufficiently tested as part of Nokia’s system verification.
| Performance measurement verification gap | Defect escaped as the specific customer use case or configuration was not known or could not be tested in the PET lab.
| Limitation of test framework or environment | Defect escaped due to test environment limitations, such as test needs an exact replica of the customer E2E network. This can include competitor equipment or using many 100’s UE, each with its own unique fading pattern.
| Test automation gap | Defect escaped due to missing testcase in CRT, either testcase is missing completely or testcase has not yet been automated.
| Test did not execute the planned scenario | A scenario which would have caught the defect was planned but was not executed in a specific release.
| Not reproducible in Nokia lab - can be detected in live network | The probability of detecting this specific fault is very low and requires the scale of a live network to increase the probability of detection.
System Verification Non-Functional Testing | Performance testing gap | Typically shows as CPU, memory or I/O issues or KPI/counter degradation, sometimes leading to resets. Load tool support is missing, PET testing not performed with the exact feature combination or traffic load, similar to customer networks.
| Robustness/stability test gap | Robustness defects are typically caused by an unexpected event or corner cases, such as network disconnects/reconnects, high network latency or high packet loss. Stability defects not detected during testing with high traffic load. Testing not performed with the exact feature combination or traffic load, similar to customer networks.
| Limitation of test framework or environment | Defect escaped due to test tool limitations, features could not be tested, insufficient load/capacity or simulator limitations
| Test automation gap | Defect escaped due to missing testcase in CRT, either testcase is missing completely or testcase has not yet been automated.
| Testcase was not executed | A specific customer scenario or feature combination, which would have detected the defect was, either not included in test plan or not executed.
Collaboration with Suppliers | Delivery failure | The delivery from the supplier was unacceptable in terms of content or quality, including software, specifications or test data.
| Lack of specification | Defect is caused by a missing or insufficiently detailed specification, either originating in Nokia or with the supplier.
| Documentation failure | There was an error in the user documentation provided with the 3rd party software.
| Implementation failure | The 3rd party software has an error in the implementation of the requirements.
| Lack of testing | The software delivered by the supplier was not sufficiently tested.
| Missing requirement | A feature/function expected in the software was not delivered.
| Project management | The committed features/functions were not delivered on the agreed date.
| 3rd party software limitations | The 3rd party software has a limitation or constraint. This can be a functional constraint or a non-functional constraint such as performance, scalability etc.

## HarmonizedValues
RCA Values
Requirements | Changing Requirement | Customer specific Configuration/traffic requirements not accounted for | Missing Requirement | Incorrect Requirement | Unclear Requirement | Misunderstood Customer Requirement | Late added Feature(s) | Standards Interpretation Error
Architecture | Interworking error - feature or component interaction. | Memory consumption error | CPU overload error | Software robustness error | Stability error | Architecture gap | Architecture specification error
High_Level_Design | Hardware compatibility | 3rd Party compatibility / interoperability | Legacy interaction error | High level design missing/gap | Design error
Low_Level_Design | Low level design missing/gap | Deficient design/ design Error | Design knowledge, skills, competence (timer management, buffer handling, etc.)
Code | Code too complex | Coding logic error | Code language knowledge/expertise | Coding standards violations | Implementation missing | Implementation error
User_Documentation_including_Release_Note | Incorrect information used to create End-User Documentation | Missing content/ step in procedure | Missing detailed content (delivered content not sufficient from users PoV) | Outdated content | Language error | Incorrect information filled in Change Note | Inconsistency within the same customer document | User documentation not tested
Configuration_and_Fault_Management | Build error/ incorrect version | Merge error | Missed defect inheritance or porting process error
Collaborated_Mode_with_Suppliers | Delivery failure | Lack of specification | Documentation failure | Implementation Failure | Lack of testing | Missing requirement | Project management | 3rd party software limitations
EDA Values
Technical_Reviews | Requirements not reviewed with customer | Internal requirement review gap | Architecture review gap | Design review gap | Missing analysis of impact of change | Code review gap | Test strategy review gap | Unit or component testcase review gap | Entity or integration test review gap | System testcase review gap | CuDo internal review gap
Code_Analysis_Tools | Test tools availability/ capability | Inappropriate tool usage | Insufficient use of static analyzers | Insufficient use of dynamic analyzers
Unit_Tests | Code not covered by test | Wrong check in testcase | Stubs or mocks do not reflect real world scenarios. | Objects initialized with wrong values | Error cases/paths not tested
System_Component_or_Module_Test | Functionality not covered | Feature interaction coverage gap | Corner case and error case test gap | Limitation of test framework or environment | Configuration coverage gap | Test did not execute the planned scenario
Entity_or_Integration_and_Verification_Test | Requirement coverage gap | Limitation of test framework or environment | Configuration coverage gap | Test did not execute the planned scenario | Exploratory testing (negative, sequence, abnormal, boundary, corner case) gap
System_Verification_Functional_Test | Network or solution verification testing gap | Regression test gap | Configuration coverage gap | Requirement coverage gap | Feature interaction coverage gap | Exploratory testing (negative, sequence, abnormal, boundary, corner case) gap | Testing of UE software | Insufficient Testing of 3rd Party SW/HW | Performance measurement verification gap | Limitation of test framework or environment | Test automation gap | Test did not execute the planned scenario | Not reproducible in Nokia lab - can be detected in live network
System_verification_Non_Functional_Testing | Performance testing gap | Robustness/stability test gap | Limitation of test framework or environment | Test automation gap | Testcase was not executed.
Collaborated_Mode_with_Suppliers | Delivery failure | Lack of specification | Documentation failure | Implementation failure | Lack of testing | Missing requirement | Project management | 3rd Party software limitations
RCA Improvement Actions
Requirements Improvement | Architecture Improvement | High-Level Design Improvement | Low-Level Design Improvement | Coding Quality Improvement | User Documentation (including Release Note) Improvement | Configuration and Fault Management Improvement | Knowledge/ Expertise/ Training Improvement
EDA Improvement Actions
Technical Reviews Improvement | Code Analysis Tools Improvement | Unit Test Improvement | System Component / Module Test Improvement | Entity/ Integration and Verification Test Improvement | System Verification Functional Test Improvement | System Verification Non-Functional Testing Improvement