## Sheet1
PRID | PRTitle | PRSeverity | JiraIssueId | JiraIssueParentId | PRAttached | JiraIssueType | JiraIssueCaseType | JiraIssueStatus | JiraIssueOverDue | JiraIssueOpenDays | JiraIssueCreatedDate | JiraIssueParentCreatedDate | JiraIssueResolutionDate | JiraIssueParentResolutionDate | JiraIssueDueDate | JiraIssueAssignee | PRRcaEdaAssessor | JiraIssueAssigneeTribe | JiraIssueAssigneeSquadGroup | JiraIssueAssigneeSquadGroupLead
PR629647 | [SBTS22R2][PET][CLOUD][ASOD][AEUB][eCPRI][4CC] PM Counters stopped pegging | B - Major |  |  | PR629843,PR634560 | Analysis subtask | RCA | Open | No | 2 | 2022-03-04 | 2022-03-04 | 2022-03-06 | 2022-03-06 | 2022-03-19 | Shen, Dan 1. (NSB - CN/Hangzhou) | Wang, Fuqiang-Frank (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP SW | NSB MN RAN ECP RD&Pz RCP SW Messaging SG | Wang, Fuqiang-Frank (NSB - CN/Hangzhou) | MNRCA-48799 | MNRCA-48798
PR636274 | [5G][QT][vDU][FDD][NSA]Commisison issue due to WaitMinDeploymentReady failed with getPodReadinessInfo of oamext pod error | B - Major |  |  |  | Analysis subtask | RCA | Open | No | 4 | 2022-03-02 | 2022-03-02 | 2022-03-06 | 2022-03-06 | 2022-03-17 | Chen, Sijie (NSB - CN/Hangzhou) | Lu, Shunlong (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP RMW&eSW | NSB MN RAN ECP RD&Pz RCP RMW&eSW N&T SG | Lu, Shunlong (NSB - CN/Hangzhou) | MNRCA-48743 | MNRCA-48742
PR635549 | [SMOKE][CU][TDD][RCPCUINT]E1 setup failed during commission | B - Major |  |  |  | Analysis subtask | RCA | Open | No | 4 | 2022-03-02 | 2022-03-02 | 2022-03-06 | 2022-03-06 | 2022-03-17 | Wang, Pei-Emily (NSB - CN/Hangzhou) | Shi, Ling (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP RMW&eSW | NSB MN RAN ECP RD&Pz RCP RMW&eSW TRH1 SG | Shi, Ling (NSB - CN/Hangzhou) | MNRCA-48741 | MNRCA-48740
PR628575 | [SMOKE][CU][TDD][RCPCUINT]CU VNF deployment failed as VM process failed | B - Major |  |  |  | Analysis subtask | RCA | Open | No | 4 | 2022-03-02 | 2022-03-02 | 2022-03-06 | 2022-03-06 | 2022-03-17 | Ling, Xiao 1. (NSB - CN/Hangzhou) | Lu, Shunlong (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP RMW&eSW | NSB MN RAN ECP RD&Pz RCP RMW&eSW N&T SG | Lu, Shunlong (NSB - CN/Hangzhou) | MNRCA-48739 | MNRCA-48738
PR636028 | [vRAN2.0][ne3sagent] ne3sagent pipeline autobump job failed due to error log: out of memory at line 1 | B - Major |  |  |  | Analysis subtask | RCA | Open | No | 6 | 2022-02-28 | 2022-02-28 | 2022-03-06 | 2022-03-06 | 2022-03-15 | Liu, Yuanjun (NSB - CN/Hangzhou) | Cheng, Rongshu (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP SW | NSB MN RAN ECP RD&Pz RCP SW HA&OI SG | Cheng, Rongshu (NSB - CN/Hangzhou) | MNRCA-48647 | MNRCA-48646
PR634806 | [CBTS22R2][vCU][AIC][OCP][PET][CB007025-5G] lwsd restart during stability test | B - Major |  |  | PR634807 | Analysis subtask | RCA | Open | No | 9 | 2022-02-25 | 2022-02-25 | 2022-03-06 | 2022-03-06 | 2022-03-12 | Liu, Yuanjun (NSB - CN/Hangzhou) | Cheng, Rongshu (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP SW | NSB MN RAN ECP RD&Pz RCP SW HA&OI SG | Cheng, Rongshu (NSB - CN/Hangzhou) | MNRCA-48598 | MNRCA-48597
PR633520 | [5G00][CIT][vDU]CMP will be stuck after first CMP IR | B - Major |  |  | PR634602 | Analysis subtask | RCA | Open | No | 9 | 2022-02-25 | 2022-02-25 | 2022-03-06 | 2022-03-06 | 2022-03-12 | Kaukanen, Osmo (Nokia - FI/Espoo) | Kenttamies, Samuli (Nokia - FI/Espoo) | MN RAN ECP RD&Pz SW | MN RAN ECP RD&Pz SW RCP SG | Kenttamies, Samuli (Nokia - FI/Espoo) | MNRCA-48596 | MNRCA-48595
PR631904 | [5G22R2_AiC][ST][CB001719] oamext-cnumserver container abnormal restart | B - Major |  |  |  | Analysis subtask | RCA | Open | No | 9 | 2022-02-25 | 2022-02-25 | 2022-03-06 | 2022-03-06 | 2022-03-12 | Kaukanen, Osmo (Nokia - FI/Espoo) | Kenttamies, Samuli (Nokia - FI/Espoo) | MN RAN ECP RD&Pz SW | MN RAN ECP RD&Pz SW RCP SG | Kenttamies, Samuli (Nokia - FI/Espoo) | MNRCA-48592 | MNRCA-48591
PR628361 | [5G22R2_AiC][vDU/vCU][ET][5GC002215-E] Huge Ipsec policies configure fail | B - Major |  |  |  | Analysis subtask | RCA | Open | No | 9 | 2022-02-25 | 2022-02-25 | 2022-03-06 | 2022-03-06 | 2022-03-12 | Cao, Weiqin (NSB - CN/Hangzhou) | Wu, Enping (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP RMW&eSW | NSB MN RAN ECP RD&Pz RCP RMW&eSW TRH2 SG | Wu, Enping (NSB - CN/Hangzhou) | MNRCA-48588 | MNRCA-48587
PR618577 | [UUF][vran1.0][5G21B]mannual load scf failed with CM 404 after VCU rollback from 5G21B854 to 5G21B779 | B - Major |  |  |  | Analysis subtask | RCA | Open | No | 9 | 2022-02-25 | 2022-02-25 | 2022-03-06 | 2022-03-06 | 2022-03-12 | Zhang, Lixia (NSB - CN/Hangzhou) | Cheng, Rongshu (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP SW | NSB MN RAN ECP RD&Pz RCP SW Database SG | Cheng, Rongshu (NSB - CN/Hangzhou) | MNRCA-48586 | MNRCA-48585
02316651 | Command calendar monthly scli-batch tasks can not be scheduled | B - Major |  |  |  | Analysis subtask | RCA | In Progress | No | 9 | 2022-02-25 | 2022-02-25 | 2022-03-06 | 2022-03-06 | 2022-03-12 | Shi, Yang 1. (NSB - CN/Hangzhou) | Zhong, Hua (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP SW | NSB MN RAN ECP RD&Pz RCP SW STR&SWM SG | Zhong, Hua (NSB - CN/Hangzhou) | MNRCA-48538 | MNRCA-48537
PR622189 | [QT][SBTS00][ASOE] RAT autonomous reset as recovery action, Virtual node not responding | A - Critical |  |  |  | Analysis subtask | RCA and EDA | In Progress | Yes | 53 | 2022-01-12 | 2022-01-12 | 2022-03-06 | 2022-03-06 | 2022-01-27 | Goumard, Nicolas (Nokia - FI/Espoo) | Honkalammi, Ismo (Nokia - FI/Espoo) | MN RAN ECP RD&Pz SW | MN RAN ECP RD&Pz SW RelDlv SG | Honkalammi, Ismo (Nokia - FI/Espoo) | MNRCA-47558 | MNRCA-47557
PR621408 | [5G][QT][CUCNF] Alarm 70164 ETHERNET LINK FAILURE due to UPUE routing failed | B - Major |  |  | PR620857 | Analysis subtask | RCA and EDA | Closed | Yes | 50 | 2022-01-12 | 2022-01-12 | 2022-03-03 | 2022-03-06 | 2022-01-27 | Cao, Weiqin (NSB - CN/Hangzhou) | Wu, Enping (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP RMW&eSW | NSB MN RAN ECP RD&Pz RCP RMW&eSW TRH2 SG | Wu, Enping (NSB - CN/Hangzhou) | MNRCA-47556 | MNRCA-47555
PR618405 | [5G][QT][CUCNF]UeContextRelease occur when testing ul/dl data taffic test case | A - Critical |  |  | PR618099,PR617705 | Analysis subtask | RCA and EDA | Closed | Yes | 50 | 2022-01-12 | 2022-01-12 | 2022-03-03 | 2022-03-06 | 2022-01-27 | Liu, Yuanjun (NSB - CN/Hangzhou) | Cheng, Rongshu (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP SW | NSB MN RAN ECP RD&Pz RCP SW HA&OI SG | Cheng, Rongshu (NSB - CN/Hangzhou) | MNRCA-47552 | MNRCA-47551
PR611048 | [SBTS00][22R1][PET][5G][LTE][IWK][COMMONTRUNK] Snapshot does not contain all of memory/CPU data | B - Major |  |  |  | Analysis subtask | RCA | Resolved | Yes | 103 | 2021-11-04 | 2021-10-12 | 2022-02-15 | 2022-02-15 |  | Zhou, Xufeng (NSB - CN/Hangzhou) | Zhang, Hui (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP SW | NSB MN RAN ECP RD&Pz RCP SW Infra&CDC SG | Zhang, Hui (NSB - CN/Hangzhou) | MNRCA-45573 | MNRCA-44885
01757018 | [Verizon Cloud NPI 5G20B_10.1100.827 CTX] All F1 links failed to come up on CU 1330002 after upgrade to 5G20B | B - Major |  |  | PR575435 | Action for RCA |  | Resolved | Yes | 0 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-05-10 | Zhang, Chunhui H. (NSB - CN/Hangzhou) | Wang, Fuqiang-Frank (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP SW | NSB MN RAN ECP RD&Pz RCP SW Messaging SG | Wang, Fuqiang-Frank (NSB - CN/Hangzhou) | MNRCA-41946 | MNRCA-41940
01757018 | [Verizon Cloud NPI 5G20B_10.1100.827 CTX] All F1 links failed to come up on CU 1330002 after upgrade to 5G20B | B - Major |  |  | PR575435 | Action for RCA |  | Resolved | Yes | 0 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-05-10 | Song, Hongjiang (NSB - CN/Hangzhou) | Wu, Yongkang (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP SW | NSB MN RAN ECP RD&Pz RCP SW Arch | Wu, Yongkang (NSB - CN/Hangzhou) | MNRCA-41945 | MNRCA-41940
01757018 | [Verizon Cloud NPI 5G20B_10.1100.827 CTX] All F1 links failed to come up on CU 1330002 after upgrade to 5G20B | B - Major |  |  | PR575435 | Action for RCA |  | Resolved | Yes | 0 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-06-23 | 2021-05-10 | Jin, Xiaoyi (NSB - CN/Hangzhou) | Lu, Shunlong (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP RMW&eSW | NSB MN RAN ECP RD&Pz RCP RMW&eSW N&T SG | Lu, Shunlong (NSB - CN/Hangzhou) | MNRCA-41943 | MNRCA-41940
01690022 | Missing CU 1330015 PM files after upgrade to 5G20B | B - Major |  |  |  | Action for EDA |  | Closed | Yes | 179 | 2021-06-23 | 2021-05-13 | 2021-12-19 | 2021-10-13 | 2021-07-31 | Xue, Luping (NSB - CN/Hangzhou) | Zhang, Lixia (NSB - CN/Hangzhou) | NSB MN RAN ECP RD&Pz RCP SW | NSB MN RAN ECP RD&Pz RCP SW Database SG | Zhang, Lixia (NSB - CN/Hangzhou) | MNRCA-41935 | MNRCA-40782